4. Using the following table of tasks,

1. Build using MSP an mpp file including a work breakdown structure and a Gantt chart showing the project critical path.
2. What does the critical path become if Task C takes three time units?

TASK Predecessors Time Units Required

A None 1

B A 2

C A 1

D BandC 1