## 2016 Events
Stakeholder
Name of Event | Date of Event | Host | Task | Due By | Business | Artistic
MSND - Opening Night | 2016-04-01 | Company | Confirm room at BCEC | 2016-03-01 | Events | Production
[5 empty] | Devel - CP | Wardrobe
[5 empty] | Devel - Phil | Dancers
[5 empty] | Mkt | Choreography
[5 empty] | Fin | Training
[5 empty] | Exec | Artistic Director
Edu
MSND - Opening Night | 2016-04-01 | Company | Design Opening Night E Invitation | 2016-02-15 | Events | Production
[5 empty] | Devel - CP | Wardrobe
[5 empty] | Devel - Phil | Dancers
[5 empty] | Mkt | Choreography
[5 empty] | Fin | Training
[5 empty] | Exec | Artistic Director
Edu
MSND - Opening Night | 2016-04-01 | Company | Design Opening Night E Invitation | 2016-02-15 | Events | Production
[5 empty] | Devel - CP | Wardrobe
[5 empty] | Devel - Phil | Dancers
[5 empty] | Mkt | Choreography
[5 empty] | Fin | Training
[5 empty] | Exec | Artistic Director
Edu
MSND - Opening Night | 2016-04-01 | Company | Finalise Opening Night Invitation List | 2016-02-24 | Events | Production
[5 empty] | Devel - CP | Wardrobe
[5 empty] | Devel - Phil | Dancers
[5 empty] | Mkt | Choreography
[5 empty] | Fin | Training
[5 empty] | Exec | Artistic Director
Edu

## Stakeholder Data
Events | Production
Devel - CP | Wardrobe
Devel - Phil | Dancers
Mkt | Training
Fin | Artistic Director
Exec
Edu

## TL Dance Dialogues
Aesop
Beverage stock take
Beverage taking sheet - update and print
Box office roster required
Budget FOH staffing, equipment and bar
Budget review - post event
Bump in schedule
Bump in schedule / set-up
Bump out schedule
Coffee supplier bump in
Coffee supplier bump out
Coffee supplier requirements
Collect Bars and Install
Dry bar hire/purchase
Event Brief - issue daily
FOH Roster Finalised
FOH Staff Availability Email
Ice - pick up
Install signs - Box / Bar / Costume / Coffee
Neighbourhood briefing ?
Order Bars
Order float and EFTPOS from finance
Order Pipe and Drape for Green Room
Permits - review folder and update
Pipe and Drape Install Green Room
Pipe and Drape Removal Green Room
Portable PA for Green Room music
Reconcilliations
Return Bars
Review and update staff folder
Review and update staff task lists
Schedule de-brief meeting
Sign design - Bar/Box/Costume/Coffee
Signage
Site inspection
Site inspection
Snacks purchase
Social media posts
Staff manuals
Staff meals
Staff roster - availability
Staff roster - distribution
Stock take beverage
TDC - Black drape - book
TDC - Black drape - install
TDC - Black drop - removal
Templates
Timesheets
Venue contract review
Venue contracted
Venue quotes
VIP invitations

## TL Opening Night
Activation Summary
Aesop
Bar hire/purchase
Beverage control system
Beverage options
Beverage orders
Beverage requirements
Beverage stock take
Box Office roster required
Budget approved
Budget draft
Budget review
Bump in schedule
Bump in schedule / set-up
Bump out schedule
Cancellation options
Cash management
Cleaning / waste
Coffee supplier bump in
Coffee supplier bump out
Coffee supplier requirements
Collect Bars and Install
Contra Summary
Contract / cxl policy/numbers
Corporate partners ?
De-brief
Dry bar hire/purchase
EDM - finalise
EDM - send to existing DB
EDM - send to STH's
Entrée card send
Equipment hire - furniture finalise
Equipment requirements
Establish preferred suppliers
Event Brief
Event Packages Theatre
Event Packages TDC
Event run sheet distribute
Event run sheet draft
Event run sheet finalise
Final numbers
Float
Flowers
FOH Roster Finalised
FOH Staff Availability Email
Forms
Green room location/require
Guest Lists
Ice - requirements/delivery
Music iPod?
Mutual Event Promotion with Partners
Neighbourhood briefing
Opening Night Invitation Design
Opening Night Invitation List Finalised
Opening Night Invitation List Review
Opening Night Invitations Sent
Operation folder
Order Bars
Order Pipe and Drape for Green Room
PA / speeches/music
Permits
Pipe and Drape Install Green Room
Pipe and Drape Removal Green Room
Production finalised
Production requirements
Reconcilliations
Return Bars
Signage
Site inspection
Site inspection
Snacks purchase
Social media posts
Staff manuals
Staff meals
Staff roster - availability
Staff roster - distribution
Stock take beverage
TDC - Black drape - book
TDC - Black drape - install
TDC - Black drop - removal
Templates
Timesheets
Venue contract review
Venue contracted
Venue quotes
VIP invitations