## BIDMC (2)
| Planning Process | [6 empty] | Field Work | [5 empty] | Reporting Process | [6 empty] | Audit Committee
Projected and actual | Pre kick-off call with specialist for audit. | Draft Scope | Kickoff Meeting with Client | Complet Scoping Documents: Audit Scope and objectives , Audit Approach, Timinig | Final Scope documents | Draft Report | Document Request List Sent to Client | Setup all client meetings / interviews | Issue request lists | Setup weekly status calls | Setting up Field work | Fielwork completed | Fieldwork Closing Meeting | Draft Report Prepared | Final Reviewed Draft Report - Internal | PwC shares draft report with client stakeholders / Discusses report content with client stakeholders | Management provides feedback on report, including Management’s responses | Finalized report & responses shared with VP owner | Finalize Report | Report Shared with COO/ CFO | Pre-BCAR Meeting | BCAR Mailing | BCAR Meeting | Specialist on BCAR meeting invite?
2015-12-25
2015-10-08
Projected | 2015-11-25 | 2015-12-16 | 2015-12-09 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-23 | 2016-01-06 | 2016-01-09 | 2016-01-13 | 2016-01-20 | 2016-01-20 | 2016-02-03 | 2016-02-03 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-24 | 2016-03-02
Actual | 10/8/2015 | 10/8/15 | 11/2/2015 |  |  | Not yet started | Complete - 10/8/15 | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-02-23 | 2016-02-24 | 2016-03-02
| FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE
Projected | 2015-11-25 | 2015-12-16 | 2015-12-09 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-23 | 2016-01-06 | 2016-01-09 | 2016-01-13 | 2016-01-20 | 2016-01-20 | 2016-02-03 | 2016-02-03 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-24 | 2016-03-02
Actual | Complete | Complete | 11/17/2015 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-02-23 | 2016-02-24 | 2016-03-02
Projected | 2015-11-25 | 2015-12-16 | 2015-12-09 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-23 | 2016-01-06 | 2016-01-09 | 2016-01-13 | 2016-01-20 | 2016-01-20 | 2016-02-03 | 2016-02-03 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-24 | 2016-03-02
Actual | Complete | In progress | 2015-12-03 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-02-23 | 2016-02-24 | 2016-03-02
Projected | 2015-11-25 | 2015-12-16 | 2015-12-09 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-23 | 2016-01-06 | 2016-01-09 | 2016-01-13 | 2016-01-20 | 2016-01-20 | 2016-02-03 | 2016-02-03 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-24 | 2016-03-02
Actual | Complete | Complete | 10/29/15 |  |  | Not yet started | Completed 11/9/15 | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-02-23 | 2016-02-24 | 2016-03-02
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | January (TBD) |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | 2015-12-08 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | Not yet scheduled |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | Not yet scheduled |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | 2015-12-02 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | January (TBD) |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | In progress | 2015-12-15 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-02-24 | 2016-03-16 | 2016-03-09 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-23 | 2016-04-06 | 2016-04-09 | 2016-04-13 | 2016-04-20 | 2016-04-20 | 2016-05-04 | 2016-05-04 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-25 | 2016-06-01
Actual | Complete | Complete | Complete 11/17/15 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-05-24 | 2016-05-25 | 2016-06-01
Projected | 2016-06-01 | 2016-06-22 | 2016-06-15 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-29 | 2016-07-13 | 2016-07-16 | 2016-07-20 | 2016-07-27 | 2016-07-27 | 2016-08-10 | 2016-08-10 | 2016-08-17 | 2016-08-17 | 2016-08-17 | 2016-08-31 | 2016-09-07
Actual | Complete | Not yet started | 2015-12-15 |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-08-30 | 2016-08-31 | 2016-09-07
Projected | 2016-06-01 | 2016-06-22 | 2016-06-15 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-29 | 2016-07-13 | 2016-07-16 | 2016-07-20 | 2016-07-27 | 2016-07-27 | 2016-08-10 | 2016-08-10 | 2016-08-17 | 2016-08-17 | 2016-08-17 | 2016-08-31 | 2016-09-07
Actual | Complete | Not yet started | Not yet scheduled |  |  | Not yet started | Not yet started | [7 empty] | Not yet started | Not yet started | Not yet started |  | Not yet started |  | 2016-08-30 | 2016-08-31 | 2016-09-07
Formulas:
Final Scope documents = [BCAR Meeting]-70
Draft Report = [BCAR Meeting]-70
Document Request List Sent to Client = [BCAR Meeting]-70
Field Work = [Setting up Field work]-21
Issue request lists = [Setting up Field work]-21
Setup weekly status calls = [Setting up Field work]-21
Setting up Field work = [BCAR Meeting]- 70
Fielwork completed = [Setting up Field work]+14
Fieldwork Closing Meeting = [Fielwork completed]+3
Reporting Process = [BCAR Meeting]-49
Final Reviewed Draft Report - Internal = [BCAR Meeting]-42
Finalize Report = [BCAR Mailing]-14
Report Shared with COO/ CFO = [BCAR Meeting]-21
Audit Committee = [BCAR Meeting]-21
Planning Process = [BCAR Meeting]-98
Draft Scope = [BCAR Meeting]-77
Kickoff Meeting with Client = [BCAR Meeting]-84
Not yet started = [BCAR Meeting]-42